# AB 354 Implementation Checklist and Suggested Activities for Local Health Departments

### TIMELINE: february- JUNE 2012

## Private ProviderS

## Meet with local adolescent health care providers and provider groups.

## Develop Targeted mailings/email blasts to providers in area. Key messages include:

## Recall patients that haven’t had Tdap,

## Order enough Tdap and other adolescent vaccines to accommodate increased adolescent visits,

## Clearly document Tdap.

## Encourage providers to ensure patients are up-to-date with other recommended immunizations, including flu, 3 HPV, meningococcal, 2 MMR, and 2 varicella.

## CAIR Report: Local health departments (LHD) and providers can print lists from CAIR of patients due for Tdap to assist in reminder/recall– consider printing reports for area providers.

## Promote use of auto-dialer messages for those with capability (www.shotsforschool.org/providerinfo).

## Share materials for patients with providers (www.shotsforschool.org/providerinfo).

## Be aware of local promotion by pharmaceutical representatives.

## Media

## Work with your local press office/PIO to draft news releases.

## Schedule Health Officer interviews with local media.

## Approach local radio and television stations for PSAs, feature stories or other airtime.

## Develop innovative media relationships (bus signs, movie theater ads, etc.).

## Develop customized talking points for your jurisdiction.

## Partner with local businesses to promote AB354.

## Public Clinics

## Plan summer and back-to-school clinics.

## Determine optimal locations and times for clinics.

## Ensure that sufficient staff is available during these times and summer vacation schedules are adjusted as needed. Order additional vaccine at least 4 weeks prior to “Back to School” rush. Ensure adequate storage space is available in refrigerator.

## Advertise LHD clinic availability on website and in media.

## Partner with community health centers to accommodate increased demand from under-insured or uninsured adolescents.

## Schools

## Discuss implementation local school districts and private schools.

## Decide on frequency and type of communications needed with schools.

## Continue to distribute stickers and PBE forms.

## If school has computerized system, check whether system can accommodate new Tdap requirement.

## Schools can promote AB354 implementation by

## Working with PTA,

## Sending out mailers,

## Auto-dialer messages,

## Placing messages on marquees,

## Posting web banners and information on websites,

## Including a message on the school calendar.

## OTHER SUGGESTIONS

## Create talking points for staff to provide uniform messages.

## Post Tdap information, tools, and links to shots for school website on LHD website (www.shotsforschool.org).

## Collaborate with other LHD programs that also work with adolescents, such as MCAH, CHDP.

## Partner with community-based organizations (CBOs)that work with adolescents to get information out.

### TIMELINE: July-SEPTEMBER

## CLINICS

## Conduct clinics.

## Coordinate clinics with school schedules to ensure that clinics are available for those who did not receive their Tdap previously.

## Locate other clinic sources such as community health centers or pharmacies as alternate resources to LHD clinics.

## Closely monitor vaccine inventory and place additional vaccine orders if necessary.